## Product Log
ID | Story | Responsible Person | Priority | Time Estimation | Status | Week No | Ideal Work Left(Hours) | Actual Work Left(Hours)
1 | Collection of sprites | Celebi Murat | 1 | 2 | Completed | 0 | 110 | 110
2 | Collection of musics | Burak Tutanlar | 1 | 3 | Completed | 1 | 88 | 100
3 | Reading levels from text file | Cholpon Abdyzhaparova and Ugur Ozkan | 1 | 5 | Completed | 2 | 66
4 | Creating game window | Burak Tutanlar | 1 | 4 | Not completed | 3 | 44
5 | Creating main menu | Cholpon Abdyzhaparova | 1 | 4 | Not completed | 4 | 22
6 | Creating visual representation of enemies | Celebi Murat | 2 | 2 | Not completed | 5 | 0
7 | Creating visual representation of player | Ugur Ozkan | 2 | 5 | Not completed
8 | Creating visual representation of levels | Umut Uzgur | 2 | 7 | Not completed
9 | Creating visual representation of bullet | Umut Uzgur | 2 | 3 | Not completed
10 | Creating visual representation of barrier | Ugur Ozkan | 2 | 2 | Not completed
11 | Enemy movement | Celebi Murat | 3 | 8 | Not completed
12 | Player movement | Burak Tutanlar | 3 | 4 | Not completed
13 | Bullet movement | Umut Uzgur | 3 | 6 | Not completed
14 | Player attack | Umut Uzgur | 4 | 3 | Not completed
15 | Enemy attack | Celebi Murat | 4 | 3 | Not completed
16 | Bullet collision | Umut Uzgur | 5 | 2 | Not completed
17 | Human interaction | Ugur Ozkan | 5 | 9 | Not completed
18 | Creating scoreboard | Cholpon Abdyzhaparova | 6 | 5 | Not completed
19 | Check for win/lose conditions | Cholpon Abdyzhaparova | 6 | 2 | Not completed
20 | Creating level result frame | Cholpon Abdyzhaparova | 6 | 2 | Not completed
21 | Transition to next level | Ugur Ozkan | 7 | 1 | Not completed
22 | Adding sounds | Burak Tutanlar | 8 | 10 | Not completed
23 | Enemy animation | Celebi Murat | 8 | 6 | Not completed
24 | Player animation | Burak Tutanlar | 8 | 4 | Not completed
25 | Barrier animation | Ugur Ozkan | 8 | 2 | Not completed
26 | Creating options menu | Cholpon Abdyzhaparova | 9 | 6 | Not completed

## Iteration0
ID | Story | Responsible Person | Time Estimation | Completed(%)
1 | Collection of musics | Burak Tutanlar | 3 | 100%
2 | Collection of sprites and organization of github | Çelebi Murat | 2 | 100%
3 | Creation of map and level logic | Uğur Özkan | 2.5 | 100%
4 | Reading levels from text file | Cholpon Abdyzhaparova | 2.5 | 100%

## Iteration1
ID | Story | Responsible Person | Time Estimation | Completed(%)
4 | Creating main frame | Burak Tutanlar | 4 hours | 0%
5.1 | Creating main menu panel | Cholpon Abdyzhaparova | 2 hours | 0%
5.2 | Adding buttons to main menu | Cholpon Abdyzhaparova | 1.5 hours | 0%
5.3 | Adding background to main menu | Cholpon Abdyzhaparova | 0.5 hour | 0%
6 | Creating visual representation of enemies | Çelebi Murat | 5 hours | 0%
7 | Creating visual representation of player | Uğur Özkan | 2 hours | 0%
8 | Creating level panel | Umut Uzgur | 4 hours | 0%
21 | Printing enemies and player to level panel | Uğur Özkan | 3 hours | 0%