## Product Backlog
[12 empty] | Week | Ideal Work Left | Actual Work Left
|  |  |  | Notes | [7 empty] | 0 | 48.5 | 48.5
Project Name | Space Invaders |  |  | [1] Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story. | [7 empty] | 1 | 38.8 | 43.5
Description | An arcade video game |  |  | [2] Priority does not always equal to implementation order | [7 empty] | 2 | 29.1 | 28.5
|  |  |  | [3] Time Estimation calculated as Implementation + Test + Refactoring | [7 empty] | 3 | 19.4 | 17.4
Next Available ID |  | 32 |  | [4] In-Progress tasks will be completed in other iterations but will show as "Sub-Iteration" | [7 empty] | 4 | 9.7 | 4.1
[12 empty] | 5 | 0
| Story ID [1] | Story | Priority [2] | Description | Time Estimation [3] | Status | Work Done | Work Left | Responsible Person(s) | Iteration # [4] | Sub - Iteration # [4]
| 1 | Sprite Collection | 5 | Spites that are planning to use for enemy, player, levels, and bullet will collected. | 2 | Completed | 2 | 0 | Çelebi Murat | 1 | -
| 2 | Music Collection | 5 | Musics that are planning to use in game will collected. | 2 | Completed | 2 | 0 | Burak Tutanlar | 1 | -
| 3 | Map and Level Logic | 1 | Implementation of level and map logic | 0.5 | Completed | 0.5 | 0 | Uğur Özkan | 1 | -
| 4 | Level readings | 1 | Reading level from a .txt file | 0.5 | Completed | 0.5 | 0 | Cholpon Abdyzhaparova | 1 | -
| 5 | Game window creation | 1 | Main screen of game where it will be played shall be prepared. Inluding logic | 3 | Completed | 3 | 0 | Burak Tutanlar | 2 | -
| 6 | Main menu creation | 2 | User can choose from predefined options | 3 | Completed | 3 | 0 | Cholpon Abdyzhaparova | 2 | -
| 7 | Enemy visual design | 2 | Enemies shall be represented visually | 3 | Completed | 3 | 0 | Çelebi Murat | 2 | -
| 8 | Player visual design | 2 | Player shall be represented visually | 3 | Completed | 3 | 0 | Uğur Özkan | 2 | -
| 9 | Level visual design | 2 | Levels shall be represented visually | 2 | Completed | 2 | 0 | Umut Uzgur | 2 | 4
| 10 | Bullet visual design | 3 | Bullet shall be represented visually | 2 | Completed | 2 | 0 | Çelebi Murat | 3 | -
| 11 | Barrier visual design | 5 | Barrier shall be represented visually | 2 | Completed | 2 | 0 | Umut Uzgur | 3 | -
| 12 | Enemy movement | 3 | Enemies shall move | 2 | Completed | 2 | 0 | Cholpon Abdyzhaparova | 3 | 4
| 13 | Player movement | 3 | Player shall move | 2 | Completed | 2 | 0 | Uğur Özkan | 3 | -
| 14 | Bullet movement | 4 | Bullet shall move | 2 | Completed | 2 | 0 | Burak Tutanlar | 3 | -
| 15 | Player attack | 4 | Player can shoot enemies. | 1.5 | Completed | 1.5 | 0 | Umut Uzgur | 3 | -
| 16 | Enemy attack | 4 | Enemies can shoot player | 1.5 | Completed | 1.5 | 0 | Çelebi Murat | 4 | -
| 17 | Bullet collision | 5 | Decide what will happen when bullet hits other obstacles | 2 | Completed | 2 | 0 | Umut Uzgur | 4 | -
| 18 | Human interaction | 1 | User can control player now | 2 | Completed | 2 | 0 | Uğur Özkan | 2 | -
| 19 | Scoreboard creation | 7 | Scoreboard will show points, levels, etc. | 1.5 | Completed | 1.5 | 0 | Burak Tutanlar | 4 | -
| 20 | End game logic | 6 | Will check for win / lose conditions | 1 | Completed | 1 | 0 | Cholpon Abdyzhaparova | 4 | -
| 21 | End game visual | 6 | Show whether user win / lose | 1 | In Progress | 0.9 | 0.1 | Cholpon Abdyzhaparova | 4 | -
| 22 | Level propogation | 7 | Proceed user to next level | 1 | Not Completed | 0 | 1 | Çelebi Murat | 4 | -
| 23 | Sounds | 7 |  | 1 | Not Completed | 0 | 1 | Burak Tutanlar | 4 | -
| 24 | Enemy animation | 7 | Enemies have animation | 1 | Completed | 1 | 0 | Uğur Özkan | 4 | -
| 25 | Player animation | 7 | Player has animation | 0 | Discarded
| 26 | Barrier animation | 7 | Barrier has animation | 1 | Completed | 1 | 0 | Cholpon Abdyzhaparova | 4 | -
| 27 | Option menu creation | 8 |  | 2 | Not Completed | 0 | 2 | Umut Uzgur | 4 | -
| 28 | [Issue] Entegrate human interaction | 6 | Comlete human interaction | 0.5 | Completed | 0.5 | 0 | Uğur Özkan | 4 | -
| 29 | Explosion Effect | 6 | Entities will explode | 1 | Completed | 1 | 0 | Uğur Özkan | 4 | -
| 30 | Player Life | 7 |  | 1 | Completed | 1 | 0 | Çelebi Murat | 4 | -
| 31 | [Issue] Back button | 7 |  | 0.5 | Completed | 0.5 | 0 | Burak Tutanlar | 4 | -

## Iteration1
Iteration # | 1
Start Date | 23.03.2014
End Date | 29.03.2014
Story ID | Story | Responsible Person | Time Estimation | Completed(%)
1 | Collection of sprites and organization of github | Çelebi Murat | 2 | 100%
2 | Collection of musics | Burak Tutanlar | 2 | 100%
3 | Creation of map and level logic | Uğur Özkan | 0.5 | 100%
4 | Reading levels from text file | Cholpon Abdyzhaparova | 0.5 | 100%

## Iteration2
Iteration # | 2
Start Date | 30.03.2014
End Date | 06.04.2014
Story ID | Story | Responsible Person | Time Estimation | Completed(%)
5 | Game window creation | Burak Tutanlar | 3 | 100%
6 | Main menu creation | Cholpon Abdyzhaparova | 3 | 100%
6.1 | Adding buttons to main menu |  | 2 | 100%
6.2 | Adding background to main menu |  | 1 | 100%
7 | Enemy visual design | Çelebi Murat | 3 | 100%
7.1 | Logic implementation |  | 1.5 | 100%
7.1 | Visual implementation (Printing enemies to level panel) |  | 1.5 | 100%
8 | Player visual design | Uğur Özkan | 3 | 100%
8.1 | Logic implementation |  | 1.5 | 100%
8.2 | Visual implementation (Printing player to level panel) |  | 1.5 | 100%
9 | Level visual design | Umut Uzgur | 2 | 50%
9.1 | Logic implementation |  | 1 | 0%
9.2 | Visual implementation (Printing levels to main panel) |  | 1 | 100%
18 | Human interaction | Uğur Özkan | 2 | 100%

## Iteration3
Iteration # | 3
Start Date | 07.04.2014
End Date | 13.04.2014
Story ID | Story | Responsible Person | Time Estimation | Completed(%)
10 | Bullet visual design | Çelebi Murat | 2 | 100%
11 | Barrier visual design | Umut Uzgur | 2 | 100%
12 | Enemy movement | Cholpon Abdyzhaparova | 2 | 80%
13 | Player movement | Uğur Özkan | 2 | 100%
14 | Bullet movement | Burak Tutanlar | 2 | 100%
15 | Player attack | Umut Uzgur | 1.5 | 100%

## Iteration4
Iteration # | 4
Start Date | 14.04.2014
End Date | 20.04.2014
Story ID | Story | Responsible Person | Time Estimation | Completed(%)
9 | Level visual design | Umut Uzgur | 1 | 100%
12 | Enemy movement | Cholpon Abdyzhaparova | 0.4 | 100%
16 | Enemy attack | Çelebi Murat | 1.5 | 100%
17 | Bullet collision | Umut Uzgur | 2 | 100%
19 | Scoreboard creation | Burak Tutanlar | 1.5 | 100%
20 | End game logic | Cholpon Abdyzhaparova | 1 | 100%
21 | End game visual | Cholpon Abdyzhaparova | 1 | 90%
22 | Level propogation | Çelebi Murat | 1 | 0%
23 | Sounds | Burak Tutanlar | 1 | 0%
24 | Enemy animation | Uğur Özkan | 1 | 100%
26 | Barrier animation | Cholpon Abdyzhaparova | 1 | 100%
27 | Option menu creation | Umut Uzgur | 2 | 0%
28 | [Issue] Entegrate human interaction | Uğur Özkan | 0.5 | 100%
29 | Explosion Effect | Uğur Özkan | 1 | 100%
30 | Player Life | Çelebi Murat | 1 | 100%
31 | [Issue] Back button | Burak Tutanlar | 0.5 | 100%

## Iteration5
Iteration # | 5
Start Date | 21.04.2014
End Date | 27.04.2014
Story ID | Story | Responsible Person | Time Estimation | Completed(%)